# Micro HRMS
Phase 1 Development Plan

Version 1.0  |  05 October 2026

Develop Micro HRMS in vertical slices: database, API, Angular screens, automated tests and a working demonstration for each module. This plan sequences the Phase 1 requirements into twelve steps with dependencies and measurable completion checkpoints.

## Architecture and delivery scope

Use the approved Angular and TypeScript frontend, NestJS modular monolith, PostgreSQL, TypeORM migrations, Redis, BullMQ and S3-compatible storage. Keep business logic within owned modules and expose cross-module services or contracts. Deploy stateless API containers and independently runnable workers; use REST under /api/v1 with Swagger documentation.

Phase 1 delivery covers all P0 requirements and agreed P1 items. Full statutory payroll automation, native mobile apps, biometric/GPS attendance, recruitment, performance management, advanced workflow design, payment gateways and AI capabilities remain outside this baseline.

## Indicative delivery schedule

Planning assumption: two full-time developers, QA support from early milestones and an available HR/product decision-maker. Refine this estimate after Step 1; allow contingency for unresolved payroll rules, scope changes and UAT findings.

| Period | Main outcome |
| --- | --- |
| Week 1 | Business rules, backlog and acceptance criteria |
| Weeks 2 to 3 | Foundation, tenancy, authorization and audit |
| Weeks 4 to 5 | Authentication, onboarding, organization and employees |
| Weeks 6 to 8 | Holidays, attendance and leave |
| Weeks 9 to 11 | Payroll, payslips and documents |
| Weeks 12 to 13 | Dashboards, reports and platform completion |
| Weeks 14 to 16 | Integrated hardening, UAT and pilot readiness |

## Feature completion rule

A feature is complete when its migration, API, UI, permissions, applicable audit behavior, meaningful tests and documentation are ready, and the end-to-end workflow has been demonstrated on staging.

Requirements baseline: Micro_HRMS_Phase_1_Requirements_v1.1.docx, version 1.1 dated 04 October 2026.

# 1 Finalize business rules before coding

Create a tracked backlog using requirement IDs such as AUTH-001, ATT-004 and PAY-011. Every ticket should state expected behavior, permissions, validation rules, dependencies and acceptance tests. Resolve the following decisions with the product and HR owners.

| Area | Decision needed |
| --- | --- |
| Authentication | Session/cookie or access/refresh tokens; email verification; email uniqueness across companies. |
| Reporting hierarchy | Direct reports or descendants; no-manager approval fallback; self-approval rules. |
| Attendance | Late/half-day thresholds, missing checkout, cross-midnight handling and correction dates. |
| Leave | Leave year, credits, basic carry-forward, half-days, overlaps and approved cancellation. |
| Payroll | Pay period, proration, rounding, loss of pay, mid-period salary changes and corrections. |
| Infrastructure | Hosting, object storage, email provider, file limits and backup retention. |
| Launch scope | Agreed P1 features and whether CSV employee import is mandatory. |
| Platform operations | Suspension, support access, retention and tenant deletion/export procedures. |

Completion checkpoint. An agreed business-rule register, prioritized backlog and acceptance criteria exist. Unresolved decisions identify their affected tickets.

# 2 Establish the project foundation

Create apps/web for Angular, apps/api for NestJS, apps/worker for BullMQ, packages/contracts for shared API types where useful, and docs for architecture, business rules and runbooks.

Set up local PostgreSQL, Redis and S3-compatible storage, TypeORM migrations and development/test seed data. Never enable synchronize=true in production.

Configure environment validation, formatting, linting, type checks, builds and CI.

Establish /api/v1, Swagger, DTO validation, consistent errors, structured logs, request IDs and health/readiness endpoints.

Build Angular layouts, API integration, reactive forms and reusable table, filter, pagination, status and feedback components.

Deploy to staging early so every milestone can be demonstrated.

Completion checkpoint. A developer can start the application from documented instructions, apply migrations and deploy a passing build to staging.

# 3 Build tenant isolation authorization and audit

Establish these controls before introducing employee or payroll data. All later modules depend on this foundation.

Resolve trusted tenant context from authenticated identity, never solely from a request-supplied tenant ID.

Scope persistence access by tenant and define tenant-aware uniqueness constraints and indexes.

Prevent records from referencing another tenant's employee, department or other resource.

Implement Admin/HR, Manager and Employee permissions, with separate Platform Admin access and self/team/company resource checks.

Record audit events with safe metadata and restricted access; exclude secrets and unnecessary sensitive information.

Scope cache keys, file access and background jobs by tenant, and introduce tenant status and subscription-readiness fields.

Create reusable automated test fixtures with two tenants and all primary roles.

Completion checkpoint. Tests prove that users cannot read, change, export or download another tenant's data, including through manipulated resource IDs.

# 4 Implement authentication and company onboarding

Coverage: AUTH-001 to AUTH-008 and relevant security requirements. Build the complete account lifecycle before employee self-service.

Register a tenant and its first administrator atomically.

Implement sign-in, sign-out and session renewal using the agreed authentication design.

Support password resets and expiring, single-use employee invitations.

Revoke access when users are disabled or terminated; apply authentication rate limits and relevant audit events.

Guide a new administrator into company setup.

Introduce the email provider interface and BullMQ delivery now because invitations and resets depend on them. Make delivery failures observable and recoverable.

Completion checkpoint. A company can register and activate an invited user without developer intervention. Expired/reused tokens and revoked sessions are rejected.

## Implementation boundary

Keep controllers thin and place business rules in application/domain services. Cross-module calls use exported services or deliberate read models, not unrestricted access to another module's repositories. Keep business-critical invariants transactional; queue retryable side effects after successful business changes.

# 5 Implement organization and employee management

Coverage: ORG-001 to ORG-007, EMP-001 to EMP-010 and role/resource permissions. Organization masters precede employee assignments.

## Organization configuration

Company profile, logo, timezone, currency and date format.

Departments, designations and locations, with archive behavior that preserves historical references.

Work week, default working hours and attendance thresholds.

Financial/payroll period configuration. Archived masters cannot be assigned to new records.

## Employee management

Employee creation, profile tabs, search, filters and pagination; employee codes unique within each tenant.

Personal, employment and emergency details, with protected bank and identifier information.

Reporting-manager assignments and hierarchy validation.

Invited, Active, On Notice and Inactive/Terminated statuses.

Explicitly allowed employee self-service edits, invitations and access revocation on termination.

CSV import with row-level validation if included in launch scope.

Completion checkpoint. HR can onboard, assign, invite and deactivate employees while preserving history. Managers and employees see only permitted records and fields.

# 6 Implement holidays and shared calendar calculations

Coverage: HOL-001 to HOL-004. Calendar rules are a shared dependency of attendance, leave and optional payroll loss-of-pay calculations.

Build company-wide and location-specific holidays, applicability rules and duplicate handling.

Establish common logic for tenant-local business dates, working days, weekly offs and applicable holidays.

Define full-day and half-day units and use the same calendar logic across attendance and leave.

Completion checkpoint. Tests cover location-specific holidays, weekends, timezone boundaries and date ranges crossing months or years.

## Data conventions

Store timestamps in UTC and retain work_date separately for business-day semantics. Use a consistent externally safe identifier strategy. Preserve attendance, payroll, approvals and audit history when employees or master records are archived.

# 7 Implement attendance and regularization

Coverage: ATT-001 to ATT-010. Build on employee eligibility, tenant timezone and the shared calendar.

Implement check-in and check-out, followed by worked-duration and attendance-status calculations.

Add personal daily/monthly views, manager team views and HR company views.

Create employee correction requests and Manager/Admin approval or rejection.

Allow authorized HR adjustments with mandatory reasons and preservation of original/audit information.

Add workflow notifications and audit events.

Enforce database uniqueness to prevent conflicting attendance records during concurrent or repeated submissions.

Completion checkpoint. Duplicate submissions, missing checkout, unauthorized approvals and approved corrections behave according to the agreed rules.

# 8 Implement leave policies balances and approvals

Coverage: LEV-001 to LEV-010. Use transactional balance updates and concurrency protection throughout.

Build leave types and basic policies, entitlements, initial credits and audited adjustments.

Track credited, used, pending/blocked and available quantities.

Support full-day and half-day requests, holiday/weekend exclusion and overlapping-request validation.

Implement approval, rejection, pending cancellation and controlled approved cancellation with balance restoration.

Provide a team calendar that limits sensitive leave details.

Update attendance/calendar effects and send workflow notifications.

Define interactions between approved leave, existing attendance and already locked payroll.

Completion checkpoint. Concurrent requests cannot overspend a balance. Approval and cancellation update balances exactly once, and attendance and leave views remain consistent.

## Required workflow demonstrations

Demonstrate an employee checking in, requesting a correction and receiving an approval; then demonstrate leave submission, approval and cancellation with the expected balances and calendar results. Repeat permission checks for self, team, unrelated employees and another tenant.

# 9 Implement payroll calculations and payslips

Coverage: PAY-001 to PAY-012. First agree on worked examples with expected results: a full month, mid-month joining, termination, unpaid leave, salary change and manual adjustment.

Create earning/deduction components and effective-dated salary structures.

Create one payroll run per tenant/pay period and select eligible employees.

Implement calculations with decimal arithmetic throughout; apply optional loss of pay using approved rules.

Support permitted manual adjustments, review, controlled state transitions and locking.

Implement explicit authorized correction/unlock handling with audit.

Generate, publish and authorize employee access to payslips.

Preserve salary inputs, relevant calculation inputs and resulting lines so historical payroll remains reproducible.

Invalidate stale generated payslips after a permitted correction.

Completion checkpoint. Agreed examples produce exact expected totals. Locked payroll resists unauthorized changes, and employees access only their own published/locked payslips.

Full statutory PF, ESI, TDS, PT and Form 16 automation remains outside baseline scope unless separately implemented and validated.

# 10 Implement employee documents

Coverage: DOC-001 to DOC-006. The storage abstraction can be introduced earlier for company logos; employee document workflows follow here.

Build categories, upload metadata, issue/expiry dates and visibility settings.

Use private object storage with authorized download access; keep metadata and object keys in PostgreSQL.

Validate file size and type, and enforce employee/resource permissions.

Support replacement, version/archive handling and audit history.

Recover or clean up uploads when file storage and metadata creation do not both succeed.

Completion checkpoint. Changing a URL, object key or employee ID cannot expose a restricted document. Archived/versioned documents retain required history.

# 11 Complete experience reports and platform operations

Coverage: DSH, NOT, RPT, audit viewing and subscription readiness. Integrate workflow notifications as domain events become available rather than postponing all notification work to this step.

Build role-specific dashboards and a notification center with read/unread states.

Deliver CSV reports for employees, attendance, leave requests, separate leave balances, payroll totals and authorized payroll components.

Apply the same permissions to reports as to transactional screens. Queued exports recheck tenant/resource access at execution.

Complete the restricted audit viewer, tenant plan/trial/status fields and active employee usage.

Implement platform tenant suspension and explicit audited support access according to the agreed operating procedure.

Expose failed jobs and controlled retry/recovery procedures.

Completion checkpoint. Dashboard totals reconcile with source records, reports respect role scope, and failed notifications/exports can be retried safely.

# 12 Harden conduct UAT and launch a controlled pilot

Testing runs throughout development. This final milestone validates the integrated system and operational readiness.

Run unit tests for attendance, leave, payroll and authorization, plus PostgreSQL integration tests for transactions, constraints and concurrency.

Exercise end-to-end onboarding, employee exit, approvals and payroll publication.

Verify tenant isolation across APIs, files, dashboards, exports and workers.

Check responsive layouts, keyboard accessibility and agreed browsers; test performance against representative tenant/data loads.

Rehearse migrations, backup restoration and deployment smoke tests; verify retries, graceful shutdown and failure recovery.

Conduct Admin/HR, Manager and Employee UAT, then launch to a small pilot group with documented deployment, recovery and support procedures.

Completion checkpoint. All P0 and agreed P1 criteria pass, core workflows are usable, backups have been restored successfully, and no known critical/high security defect remains open.

## First milestone

Complete the agreed rulebook and a running, tenant-isolated foundation. This establishes the dependencies for attendance, leave and payroll and makes progress measurable from the start.